## Sheet1
Tasks Name |  | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Project management | Project List | 2022-11-10 | 2022-12-03 | 100% | Nguyễn Đoàn Trường Vĩ | 2022-12-01 | 2022-12-03 | 100% | Phương Dư Đức Thế
| Edit Project | 2022-11-10 | 2022-12-03 | 80% | Nguyễn Đoàn Trường Vĩ | 2022-12-01 | 2022-12-03 | 100% | Phương Dư Đức Thế | thiếu render project category
| Delete Project | 2022-11-10 | 2022-12-03 | 100% | Nguyễn Đoàn Trường Vĩ | 2022-12-01 | 2022-12-03 | 100% | Phương Dư Đức Thế
| Add member | 2022-11-10 | 2022-12-03 | 50% | Nguyễn Đoàn Trường Vĩ | 2022-12-01 | 2022-12-03 | 100% | Phương Dư Đức Thế | hiển thị ra modal nhưng không add được
| Project Detail | 2022-11-10 | 2022-12-03 | 100% | Nguyễn Đoàn Trường Vĩ | 2022-12-01 | 2022-12-03 | 100% | Phương Dư Đức Thế
| Sort Project | 2022-11-10 | 2022-12-03 | 100% | Nguyễn Đoàn Trường Vĩ | 2022-12-01 | 2022-12-03 | 100% | Phương Dư Đức Thế
| Task List | 2022-11-10 | 2022-12-03 | 100% | Nguyễn Đoàn Trường Vĩ | 2022-12-01 | 2022-12-03 | 100% | Phương Dư Đức Thế
| Create Task | 2022-11-10 | 2022-12-03 | 100% | Trường Vĩ + Đức Thế | 2022-12-01 | 2022-12-03 | 100% | Phương Dư Đức Thế
| Edit Task/Comment Task | 2022-11-10 | 2022-12-03 | 50% | Nguyễn Đoàn Trường Vĩ | 2022-12-01 | 2022-12-03 | 100% | Phương Dư Đức Thế | không render ra modal Edit Task
| Delete Task | 2022-11-10 | 2022-12-03 | 100% | Nguyễn Đoàn Trường Vĩ | 2022-12-01 | 2022-12-03 | 100% | Phương Dư Đức Thế
| Search Task | 2022-11-10 | 2022-12-03 | 50% | Nguyễn Đoàn Trường Vĩ | 2022-12-01 | 2022-12-03 | 100% | Phương Dư Đức Thế | không render ra modal search Task
User management | User List | 2022-11-10 | 2022-12-03 | 100% | Phương Dư Đức Thế | 2022-12-01 | 2022-12-03 | 100% | Nguyễn Đoàn Trường Vĩ
| Edit User | 2022-11-10 | 2022-12-03 | 100% | Phương Dư Đức Thế | 2022-12-01 | 2022-12-03 | 100% | Nguyễn Đoàn Trường Vĩ
| Delete User | 2022-11-10 | 2022-12-03 | 100% | Phương Dư Đức Thế | 2022-12-01 | 2022-12-03 | 100% | Nguyễn Đoàn Trường Vĩ
| Sort User | 2022-11-10 | 2022-12-03 | 100% | Phương Dư Đức Thế | 2022-12-01 | 2022-12-03 | 100% | Nguyễn Đoàn Trường Vĩ
Login |  | 2022-11-10 | 2022-12-03 | 100% | Phương Dư Đức Thế | 2022-12-01 | 2022-12-03 | 100% | Nguyễn Đoàn Trường Vĩ
Regsiter |  | 2022-11-10 | 2022-12-03 | 100% | Phương Dư Đức Thế | 2022-12-01 | 2022-12-03 | 100% | Nguyễn Đoàn Trường Vĩ
| Deploy lên Hosting | Trường Vĩ
| Quay Youtube demo Website | Nguyễn Đoàn Trường Vĩ